## Sheet1
Task | Tanggal Mulai | Tanggal Selesai | Status | Nama Developer
Pre processing | 2021-10-20 | 2021-10-28 | Done | Akbar
Modelling | 2021-10-30 | 2021-11-09 | Done | Yusril
Augmentasi | 2021-11-10 | 2021-11-13 | Done | Yusril
Oversampling/Downsampling | 2021-11-13 | 2021-11-24 | Done | Akbar
Pretrained/Testing Model | 2021-11-24 | 2021-12-08 | Done | Yusril
Deployment | 2021-12-08 | 2021-12-22 | Waiting | Akbar
Task | Pengerjaan
Pre processing | Modul 1
Modelling | Modul 2
Augmentasi | Modul 3
Oversampling/Downsampling | Modul 4
Pretrained/Testing Model | Modul 5
Deployment | Modul 6